## IIB
EDIS Deployment Plan
Java Prod servers: |  | NA
QA Servers (for reference and Bindings) |  | NA
RIT for firewall |  | NA
Interface Covered - |  | AirMilePoints
EG Groups - |  | Verify EG Group: es00ed09, and with 1 GB JVM heap size
S.No. | Step | Task | Description | Owner | Dependency | Duration | Start Date | End Date | Status | Remarks
1 | Prepare for Cutover |  |  | Colin | Production CR
Finalize cutover plan and checklists
Communicate cutover plan to deployment teams
Communicate go-live timeline to down streams
2 | Kafka Inbound Topic creation | Create Kafka Topic in Production server | OCRP_C02_EDIS_ALASKA_DETAILS_OUTBOUND, OCRP_C02_EDIS_ALASKA_SUMMARY_OUTBOUND | Robert
3 | Kafka Inbound Topic Verification | Verify Kafka Topic in Production server | OCRP_C02_EDIS_ALASKA_DETAILS_OUTBOUND, OCRP_C02_EDIS_ALASKA_SUMMARY_OUTBOUND | Robert
4 | Kafka Outbound Topic creation | Create Kafka Topic in Production server | ESED_C01_AirMilePoints | Robert |  | 15 mins
5 | Kafka Outbound Topic Verification | Verify Kafka Topic in Production server | Verify if the topic ESED_C01_AirMilePoints is created in Prod. | Robert |  | 15 mins
6 | Deploy IIB Application | Deploy & enable IIB application flows deployment folders: IIB /appl/spool/deploy/ESEDA IIB /appl/spool/deploy/ESEDB PS: The publisher flow used reading from Kafka Inbound Topic , then using the IIB for validations and transformation logic and then pushing the data to Kafka Outbound Topic. | ESED_AirMilePoints_OCRP_IH_Publisher | Robert |  | 15 mins
7 | Verify Production Readiness - Comms | Communicate the deployment completion |  | Colin